Integrated Infrastructure Initiative

for

Neutron Scattering and Muon Spectroscopy

(NMI3)

Joint Research Activity – JRA8

Monte Carlo simulation of 
Neutron Scattering Instruments

(MCNSI)

Budget and milestones for final contract

| Table 1. Objectives of JRA8 – MCNSI |  |  |
| --- | --- | --- |
| Task | Partners | (Bold indicates the partner with main responsibility for the task.) (Tasks T2, T6, and T7 holds more than one responsible partner. This reflects that the responsibilities within these tasks are specific to the three packages.) |
| T1 | P1 | Coordination, including start-up meeting, workshops, and MCNSI home page. |
| T2 | P1, P2, P3, P7 | Maintenance of the 3 packages (RESTRAX, McStas, VITESS), including full documentation, package home pages, user support, and incorporation of user contributions. |
| T3 | P1, P2, P3, P4, P5, P6, P7 | Intercomparison between packages – and with real experiments, including thorough reports and journal papers. (With American partners). |
| T4 | P1, P2, P3, P5 | Incorporation of common data format (NeXus) in all packages, including proper documentation. |
| T5 | P1, P2, P3, P6, P7 | Realistic simulations of samples, including definition of general expressions, implementing sample environments, samples for inelastic, quasielastic, single crystal, small-angle scattering and reflectivity, and journal papers. (with Australian partners) |
| T6 | P1, P2, P3, P4, P5, P6, P7 | Establish virtual experiment tool for selected instruments and demonstrate the use for planning of experiments, including “real” runs with end users. |
| T7 | P1, P2, P4, P5, P6 | Establish a Time-Of-Flight simulation knowledge base, including help desk, improvement of Time-Of-Flight components, and virtual experiment simulations of planned instruments. |

| Table 2. Milestones (M) and deliverables (D) of JRA8 – MCNSI |  |  |
| --- | --- | --- |
| Task | Deliverables/ Milestones |  |
| T1 | D1.1. | Kick-off meeting |
|  | D1.2. | First meeting (6 months) |
|  | D1.3. | Second meeting (12 months) |
|  | D1.4. | First Annual report. |
|  | D1.5. | Third meeting (18 months) |
|  | D1.6. | Fourth meeting (24 months) |
|  | D1.7. | Second Annual report |
|  | D1.8. | 5th meeting (30 months) |
|  | D1.9. | 6th meeting (36 months) |
|  | D1.10. | Third Annual Report |
|  | D1.11. | Fourth and Final Annual report |
|  | M1.1. | MCNSI home page ready |
| T2 | D2.1. | New release of McStas and VITESS |
|  | D2.2. | McStas and VITESS documentation and home page |
|  | D2.3. | New release of all 3 packages with NeXus format, user contributions |
|  | D2.4. | First version of RESTRAX manual |
|  | D2.6. | New release of all 3 packages, user contributions |
|  | D2.7. | RESTRAX manual finalized, updates of McStas and VITESS manuals |
|  | D2.8. | Final releases within NMI3 |
|  | D2.9. | Manuals for all packages |
| T3 | D3.1. | Conference presentation at ICNS-05 |
|  | D3.2. | Journal paper on Time-Of-Flight comparisons |
|  | D3.3. | Report on Time-Of-Flight intercomparisons |
|  | D3.5. | Report and journal paper on steady state intercomparisons |
|  | M3.1. | Strategy agreed with US partners |
|  | M3.2. | Common simulation of first TOF instrument, e.g. IRIS |
|  | M3.3. | Real TOF experiment performed, comparison with simulations |
|  | M3.4. | Common simulation on existing steady-state instrument |
|  | M3.5. | TOF error correction performed, new simulations |
|  | M3.6. | Real steady-state experiment performed, comparison |
|  | M3.7. | Steady-state error correction done |
|  | M3.8. | Convergence between results for different packages |
| T4 | M4.1. | First working version of NeXus format in all packages |
|  | M4.2. | NeXus established as a simulation data standard |
| T5 | D5.1. | Journal paper on basic principles of sample components |
|  | D5.2. | Journal paper on sample environment simulations |
|  | M5.1. | Basic principles settled, discussions with Australian partner |
|  | M5.2. | Prototype sample components of (single crystal, powder, quasielastic, inelastic dispersion, SANS, reflectivity) available in all packages |
|  | M5.3. | Concepts for sample environment part, including multiple entries |
|  | M5.4. | Prototype sample environment part |
|  | M5.5. | Sample environment part tested |
| T6 | D6.1. | Meeting (with conclusion and report) on detailed aims for virtual experiments |
|  | D6.2. | Conference presentation and journal paper on prototype virtual instrument |
|  | D6.3. | Conference presentation and journal paper on virtual instrument tools |
|  | D6.4. | Manuals and training material for virtual experiment tools at PSI, HMI, ISIS |
|  | M6.1. | Prototype virtual experiment running at one PSI instrument |
|  | M6.2. | First prototype virtual experiment running at HMI |
|  | M6.3. | First prototype virtual TOF experiment running at ISIS |
|  | M6.4. | One PSI instrument running virtual experiments for users |
|  | M6.5. | One ISIS and one HMI instrument have virtual user experiments |
|  | M6.6. | Workshop on virtual experiments with training for instrument scientists |
|  | M6.7. | Training course + material for users and students |
| T7 | D7.1. | TOF home page established |
|  | D7.2. | Journal paper on TOF simulations |
|  | M7.1. | Workshop on simulation of TOF instruments, including American partners |
|  | M7.2. | Contributions to McStas and VITESS modules identified |
|  | M7.3. | Components needed for IRIS simulations tested |
|  | M7.4. | Simulation of one instrument for ISIS 2nd target station |
|  | M7.5. | Simulations of additional ISIS 2nd target station instruments |

Connections between tasks are as follows:

- T1 (coordination) is necessary for all other tasks

- T2 forms the basis for all other tasks and uses input from T3, T4, T5, and T7

- T3 is strongly related to T2, but depends also on T4, T5, T6, and T7

- T4 depends only on T2

- T5 depends on T2, T3, and T6

- T6 depends on T2, T5, and T7

- T7 depends on T2 and T3

| Task | Action | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T1 | JRA meetings | D1.1 | D1.2 |  | D1.3 |  | D1.5 |  | D1.6 |  | D1.8 |  | D1.9 |
|  | Reports |  |  |  | D1.4 |  |  |  | D1.7 |  |  |  | D1.10 |
|  | Home page | M1.1 |  |  |  |  |  |  |  |  |  |  |  |
|  | Workshops | M3.1 | M7.1 | M5.1 |  |  |  |  |  |  | M7.8 |  | M6.6 |
| T2 | Package releases |  | D2.1 |  | D2.3 |  | D2.4 |  | D2.6 |  | D2.7 |  | D2.9 |
|  | Documentation |  | D2.2 |  |  |  | D2.5 |  |  |  | D2.8 |  |  |
| T3 | Conference presentations |  |  |  |  |  | D3.1 |  |  |  |  |  |  |
|  | Articles and reports |  |  |  |  |  | D3.2 |  |  |  | D3.3 |  |  |
|  | Strategy meeting | M3.1 |  |  |  |  |  |  |  |  |  |  |  |
|  | Simulation performed |  |  |  | M3.2 |  | M3.4 |  |  |  |  |  | M3.9 |
|  | Experiment performed |  |  |  |  | M3.3 |  |  | M3.6 |  |  |  |  |
|  | Error correction |  |  |  |  |  |  |  | M3.5 |  | M3.7 |  | M3.8 |
| T4 | NeXus installations |  | M4.1 |  |  |  | M4.2 |  |  |  |  |  |  |
| T5 | Journal articles |  |  |  | D5.1 |  |  |  |  |  | D5.2 |  |  |
|  | Workshop |  |  | M5.1 |  |  |  |  |  |  |  |  |  |
|  | Component releases |  |  |  | M5.2 |  | M5.3 |  | M5.4 |  | M5.5 |  | M5.6 |
| T6 | Strategy meeting |  | D6.1 |  |  |  |  |  |  |  |  |  |  |
|  | Conference presentations |  |  |  |  |  | D6.2 |  |  |  |  |  |  |
|  | Journal articles |  |  |  |  |  | D6.2 |  |  |  |  |  |  |
|  | Documentation |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Prototype |  | M6.1 |  | M6.2 |  | M6.3 |  |  |  |  |  |  |
|  | Virtual experiments running at facilities |  |  |  |  |  |  |  | M6.4 |  |  |  | M6.5 |
|  | Workshop and training |  |  |  |  |  |  |  |  |  |  |  | M6.6 |
| T7 | Home page |  | D7.1 |  |  |  |  |  |  |  |  |  |  |
|  | Journal articles |  |  |  | D7.2 |  |  |  |  |  |  |  |  |
|  | Workshop |  | M7.1 |  |  |  |  |  |  |  | M7.8 |  |  |
|  | Strategy settled |  |  | M7.2 |  |  |  |  |  |  |  |  |  |
|  | Components |  |  | M7.3 |  |  |  |  |  |  |  |  |  |
|  | Simulations |  |  |  | M3.2 |  | M7.4 |  | M7.5 |  | M7.6 M7.7 |  | M7.9 |

2.	Quality of the management

- 2.1	Management and competence of the participants

2.1.1 The JRA will be managed by the JRA committee (JRAC), composed of one representative from each partner. The coordinator will chair the JRAC. The JRAC will meet twice per year to discuss the current state of the project. One of these meetings will be held together with the other JRA and the NMI3 General Assembly. Every year the JRAC will submit a report to the General Assembly.

The JRA will have a Web-site which will be used to report on past activities, to disseminate the results and to announce future JRA meetings. There will be an E-mail discussion group for the users of the packages.

2.1.2 The list of participants and their competences is included as Table 4.

2.2	Justification of financing requested

2.2.1	The summary budget is listed in Table 5. Below follows comments to the budget.

It is essential that each of the three simulation packages will be supported by at least one full-time person over the full length of the JRA. With the limited budget, no money are left for the other partners, except a small seed of travel money for INFM. The limited budget also dictates that this JRA can last only 3 years.

The salary costs are adjusted on the basis of an expected 3% annual salary increase.

Travel costs reflect two meetings per year for in average 1,5 persons per partner. One additional travels to Australia is foreseen in 2004 for the MCNSI coordinator (Risø).

2.2.2	The relatively small expenses for equipment connected to acquisition of computer hardware will be covered by the partners outside the MCNSI budget.

2.2.3 	The small subcontractor cost (4 kEuro) for NPI is used for professional proof reading and language check of the RESTRAX documentation. This task is necessary but not research related, and the best value for money will be assured by having this task sub-contracted. Since VITESS and McStas already have documentation from earlier releases, the proof and language check will here be much smaller task, which should not be sub-contracted.

2.2.4 	INMF will participate mainly on a self-financing basis, while ILL, ISIS, and PSI are 100% self-financed. Details have been given above.

| Table 4. Partners of JRA8 - MCNSI |  |  |
| --- | --- | --- |
| Partner | Acronym |  |
| P1 | Risø | Organisation: Risø National Laboratory, Materials Research Department |
|  |  | Task responsible: JRA co-ordinator (T1), developer of the McStas package (T2), sample simulation (T5), virtual experiments(T6) Task participant: T3, T4, T7 |
|  |  | Research Effort: manpower, about 4 man years |
|  |  | Competence: Former European neutron user facility, long-term effort in Monte Carlo simulations of neutron scattering |
|  |  | Publications: K. Lefmann and K. Nielsen, Neutron News 10, 3, 20-23 (1999) K. Lefmann, K. Nielsen, A. Tennant, and B. Lake, Physica B 276-278, 152-153 (2000) K. Nielsen and K. Lefmann, Physica B 283, 426-432 (2000) P. Allenspach, P. Böni, and K. Lefmann, Proceedings of SPIE 4509 (2001) S. N. Klausen, K. Lefmann, D. F. McMorrow, F. Altorfer, S. Janssen, and M. Lüthy, Appl. Phys. A 74, S1508-S1510 (2002) H. Edwards, K. Lefmann, B. Lake, K. Nielsen, and P. Skaarup, Appl. Phys. A 74, S1492-S1494 (2002) P.-O. Åstrand, K. Lefmann, E. Farhi, K. Nielsen, and P. Skårup, Appl. Phys. A 74, S1511-S1513 (2002) E. Farhi, T. Hansen, A. Wildes, R. Ghosh, and K. Lefmann, Appl. Phys. A 74, S1471-S1473 (2002) |
| P2 | HMI | ### Organisation: Berlin Neutron Scattering Center, Hahn-Meitner Institut, Berlin, Germany |
|  |  | Task responsible: developer of the VITESS package (T2), sample simulations in VITESS (T5), virtual experiments in VITESS (T6), Time-Of-flight simulation knowledge base (T7) Task participant: T3, T4 |
|  |  | Research Effort: manpower engaged about 8 man-years; approximate beamtime for comparison to experiment total 1 month |
|  |  | Competence: European neutron user facility, long-term effort in Monte Carlo simulations of neutron scattering |
|  |  | Publications: F. Mezei and G. Zsigmond, Proceedings of ICANS-XIV, Starved Rock Lodge, Illinois, 113-118 (1998) D. Wechsler, G. Zsigmond, F. Streffer and F. Mezei, Neutron News 11, No. 4, 25-28 (2000) G. Zsigmond and F. Mezei, Proceedings of ECNS-II, Physica B 276-278, 106-107 (2000) D. Wechsler, G. Zsigmond, F. Streffer, J.A. Stride and F. Mezei, Proceedings of ECNS-II, Physica B 276-278 71-72 (2000) J. A. Stride, D. Wechsler, F. Mezei and H.-J. Bleif, Nucl. Instr. and Meth. in Phys. Res. A 451, 480-491 (2000) G. Zsigmond, F. Mezei, D. Wechsler and F. Streffer, Nucl. Instr. and Meth. in Phys. Res. A 457 299-308 (2001) G. Zsigmond, D. Wechsler and F. Mezei, Proceedings of ICANS-XV, JAERI, Tsukuba, Vol. I, 400-402 (2001) K. Lieutenant, H. Fritsche and F. Mezei, Appl. Phys. A 74, S1613-S1615 (2002) G. Zsigmond, K. Lieutenant, F. Mezei, Appl. Phys. A 74, S224-S225 (2002) G. Zsigmond, K. Lieutenant, F. Mezei, Neutron News 13., Issue 4, 11-14 (2002) H.N. Bordallo, K.W. Herwig, G. Zsigmond, Nucl. Instr. and Meth. in Phys. Res. A 491, 216-225 (2002) G. Zsigmond, J. M. Carpenter, F. Mezei, Proceedings of SPIE’s 47th Annual Meeting, 4785, 91-102 (2002) |
| P3 | NPI | Organisation: Nuclear Physics Institute, Rez near Prague, Czech Republic |
|  |  | Task responsible: Developer of the RESTRAX package (T2), virtual experiments in RESTRAX (T6) Task participant: T3, T4 |
|  |  | Research Effort: Staff: 24 man months paid by NPI, Beam time: ~ 15 beam days at the NPI diffractometers for measurement of mochromators/samples |
|  |  | Competence: European neutron user facility, long-term effort in Monte Carlo simulations of neutron scattering |
|  |  | Publications: - J. Šaroun and J. Kulda, Physica B 234-236, 1102-1104 (1997) - J. Šaroun, J. Kulda, Journal of Neutron Research 6, 125-133 (1997) - J. Kulda, P. Courtois, P. Flores, J. Šaroun, M. Thomas, M. Enderle and A. Monteith, SPIE proceedings 4509, 13-20 (2002) A. Wildes, J. Šaroun, E. Farhi, I. Anderson, P. Hoghoj and A. Brochier, Appl. Phys. A 74, S1452-S1454 (2002) J. Šaroun, T. Pirling and R. B. Rogge, Appl. Phys. A 74, S1489-S1491 (2002) J. Šaroun, J. Kulda, Neutron News 13, 15-19 (2002) |
| P4 | CCLRC | Organisation: Central Laboratory for the Research Councils, Didcot, UK |
|  |  | Task responsible: Time-of-Flight simulation knowledge base (T7) Task participant: T3, T6 |
|  |  | Research Effort: |
|  |  | Competence: Leading European neutron user facility, expert in time-of-flight instrumentation |
|  |  | Publications: |
| P5 | PSI | Organisation: Paul Scherrer Institut, Villigen, Switzerland |
|  |  | Task responsible: Incorporating the NeXus data format into the simulation packages (T4) Task participant: T3, T6, T7 |
|  |  | Research Effort: PSI adds 36 man months and contributes several days/year beam time on SINQ instruments, plus calculation time on the PSI high performance computer MERLIN |
|  |  | Competence: European neutron user facility, long-term effort in establishing the NeXus data format |
|  |  | Publications: M. Koennecke et al., NOBUGS Proceedings, (1997) U. Filges, Proceedings of workshop VITESS 2.0 (2001) M. Koennecke, U. Filges, NOBUGS Proceedings, (2002) |
| P6 | INFM | Organisation: Istituto Nazionale per la Fisica della Materia, Operative Group in Grenoble, France |
|  |  | Task responsible: None Task participant: T3, T5, T7 |
|  |  | Research Effort: 36 man months of INFM or associated personnel |
|  |  | Competence: Development of neutron and synchrotron instrumentation. Expertise in Monte Carlo simulations of monochromators |
|  |  | Publications: M. Sanchez del Rio, L. Alianelli, T.A. Pikuz and A. Ya. Faenov, Rev. Sci. Instrum.72, 3291-3303 (2001) L. Alianelli, M. Sanchez del Rio and R. Felici, SPIE proceedings, vol. 4509 (2001) F. Flora , S. Bollanti, A. Lai, P. Di Lazzaro, T. Letardi, A. Grilli, L. Palladino, G. Tomassetti, A. Reale, L. Reale, A. Scafati, L. Bacchetta, L.Alianelli, M. Sanchez del Rio, T.A. Pikuz, A.Ya. Faenov, SPIE proceedings, vol. 4504 (2001) P. Courtois, B. Hamelin, H. Humblot, L. Alianelli, F. Pfeiffer, Applied Physics A 74 (2002) C. Mondelli, L. Alianelli, M. Bee, A. Deriu, F. Natali, A. Paciaroni and C. Pfister, Applied Physics A 74 (2002) L. Alianelli, M. Sanchez del Rio, F. Cerrina and M. Khan, J. Synchrotron Rad. 8 1047-1050 (2001); J. Synchrotron Rad., 10, 191-192, (2003) L. Alianelli, M. Sanchez del Rio, A. Ya. Faenov, T. Pikuz, R. Felici and O. Hignette, Proceedings of 7th International Conference on X-ray microscopy, (2002) M. Sanchez del Rio, L. Alianelli, A. Ya. Faenov and T. Pikuz, Acta Cryst. A (submitted). |
| P7 | ILL | Organisation: Institut Laue-Langevin, Grenoble, France |
|  |  | Task responsible: Package intercomparison (T3) Task participant: T2, T5, T6 |
|  |  | Research Effort: |
|  |  | Competence: Leading European neutron user facility, co-developer of the McStas simulation package |
|  |  | Publications: |

- Table 5. JRA8 budget

| Partner No. | Acronym | Staff | Staff cost | Hardware | Consumables | Travel | Overheads | Total | Cost basis | % | EU contribution |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | man months | € | € | € | € | € | € |  |  | € |
| P1 | Risø | 48 | 123500 |  |  | 10000 | 126590 | 260090 | FC | 50 | 130040 |
| P2 | HMI | 48 | 128100 |  |  | 8000 | 89670 | 225770 | FC | 50 | 112890 |
| P3 | NPI | 36 | 30600 |  | (subcontr.) 4000 | 8000 | 8520 | 51120 | AC | 100 | 51120 |
| P4 | CCLRC | 36 | 0 |  |  | 0 |  | 0 |  |  | 0 |
| P5 | PSI | 24 | 0 |  |  | 0 |  | 0 |  |  | 0 |
| P6 | INFM | 24 | 0 |  |  | 5000 | 1000 | 6000 | AC | 100 | 6000 |
| P7 | ILL | 36 | 0 |  |  | 0 |  | 0 |  |  | 0 |
|  | Total | 252 | 282200 | 0 | 4000 | 31000 |  |  |  |  | 300050 |